# Salt Security Value Realization: Recommended Next Steps

Oct 26, 2026 · @Stas Kosovskiy

Prepared by Deloitte for [Client Name]. Draft for discussion.

## Executive summary

Recommendation: move Salt from "deployed" to "operated" in the next 90 days, then extend it to AI security (AI-SPM and AI Detection) by month six.

Situation. Salt Security is deployed in [Client]'s environment and is collecting data. The platform can already inventory APIs, assess posture and detect attacks.

Challenge. A deployed tool does not reduce risk on its own. Today there is no agreed plan for who acts on Salt findings, which risks come first, or how Salt supports [Client]'s growing use of AI agents and LLM applications.

What we recommend:

- Operationalize (days 0–30): validate coverage, assign owners, connect Salt to SIEM and ticketing, and close the top critical findings.

- Govern (days 30–90): agree posture policies, remediation SLAs and CI/CD checks so findings are fixed as part of normal engineering work.

- Extend to AI security (months 3–6): inventory AI agents and MCP servers, enforce AI posture policies, enable AI Detection and Response, and move high-confidence attacks to automated blocking.

Expected outcome by month six: a complete, owned inventory of APIs, agents and MCP servers; measurable reduction in critical exposure; and runtime protection for AI workloads reported to leadership monthly.

## Where you are today

We assess [Client] at Level 1 (Deployed) on a five-level maturity model, with the target of Level 4 by month six. The current-state column is our working hypothesis and should be confirmed in a 2-hour discovery workshop.

| Level | What it looks like | [Client] today (to validate) | Target |
| --- | --- | --- | --- |
| 1. Deployed | Salt installed and collecting data; findings reviewed ad hoc | Yes | Month 0 |
| 2. Operated | Coverage verified, asset owners named, alerts in SIEM, findings in ticketing | Partial / unknown | Month 1 |
| 3. Governed | Posture policies and remediation SLAs enforced; checks in CI/CD | No | Month 3 |
| 4. AI-aware | AI agents and MCP servers inventoried; AI posture policies and AI Detection live | No | Month 6 |
| 5. Protecting | Automated blocking of high-confidence attacks; continuous improvement | No | Month 9+ |

Questions to answer in the discovery workshop

- ☐ Which cloud accounts, gateways and repositories are connected, and which are not?

- ☐ Is Salt in monitor-only mode, or is any blocking enabled?

- ☐ Where do Salt alerts go today, and who reviews them?

- ☐ How many critical and high posture findings are open, and who owns them?

- ☐ Which business units are building AI agents, LLM apps or MCP servers?

- ☐ Which AI guardrails or AI gateways are already in place?

## First 30 days: quick wins

Eight actions turn the existing deployment into visible risk reduction within a month, with no new tooling.

| # | Action | Why it matters | Owner |
| --- | --- | --- | --- |
| 1 | Coverage gap review: compare connected accounts, gateways and repos against the CMDB | Salt only protects what it sees | Salt owner + Cloud team |
| 2 | Onboard missing sources (Cloud Connect, GitHub Connect, gateway collectors) | Closes blind spots, including MCP servers in code | Cloud / platform |
| 3 | Identify crown-jewel APIs (payments, PII/PHI, auth) and tag them in Salt | Focuses effort on business-critical exposure | Security + business owners |
| 4 | Assign an owner to every crown-jewel API and every discovered MCP server | Findings without owners are never fixed | App leads |
| 5 | Triage the top 20 critical/high posture findings and open tickets | First measurable risk reduction | Salt owner + app teams |
| 6 | Review shadow and zombie APIs; decommission or onboard | Removes unmanaged attack surface | App teams |
| 7 | Integrate Salt alerts with SIEM/SOAR and write 3 starter runbooks | Alerts reach the SOC in its normal workflow | SOC |
| 8 | Produce a baseline executive dashboard | Sets the starting point for value reporting | Salt owner |

## Recommended roadmap

Five phases over about 26 weeks, building on the existing Salt deployment. Phases overlap where work can run in parallel, and each ends at a gate the steering committee signs off. Automated blocking starts only after AI detection is tuned.

Recommended roadmap · 5 phases over 26 weeks

Assessment and operationalization come first; AI detection starts in week 10, and blocking only in week 18 once detections are tuned.

### Phase 1 — Assess (weeks 0–3)

Objective: establish a fact-based picture of what Salt covers today, what it has found, and who acts on it, so the rest of the roadmap targets the biggest gaps.

Key activities

- Discovery workshop (2 hours) with security, cloud, SOC and two to three app teams.

  - Walk through the current-state questions in this document.

  - Review the Salt console live: connected sources, inventory, open findings, alert settings.

- Coverage gap analysis.

  - Export the Salt inventory and compare it with the CMDB, cloud account list, API gateway list and repository list.

  - Classify every gap: not connected, partially connected (e.g. no traffic), or out of scope.

- Findings baseline.

  - Count open posture findings by severity, application and age.

  - Count shadow and zombie APIs and sensitive-data exposures.

- Process baseline.

  - Map where Salt alerts go today, who reviews them and how fast.

  - Check whether any blocking is enabled and on which apps.

- AI landscape scan.

  - Interview business units building AI agents, LLM apps or MCP servers.

  - List existing AI guardrails, AI gateways and model platforms in use.

- Scope and ownership.

  - Confirm the crown-jewel application list (payments, PII/PHI, authentication, core business APIs).

  - Name the Salt platform owner and app-team champions.

Deliverables

- Current-state assessment and maturity score (Level 1–5).

- Coverage gap register with owners and target dates.

- Prioritized remediation backlog (top 20 findings).

- AI asset landscape summary.

- Confirmed scope, RACI and steering committee schedule.

Who is involved: Deloitte team (lead), Salt platform owner, cloud/platform lead, SOC lead, selected app-team leads, CISO for sign-off.

Gate — exit criteria

- ☐ Current state and maturity level validated by [Client].

- ☐ Coverage gap register agreed, every gap with an owner.

- ☐ Crown-jewel list and AI scope signed off.

- ☐ Salt platform owner named with dedicated capacity.

### Phase 2 — Operationalize (weeks 2–8)

Objective: close coverage gaps and connect Salt to the teams and tools that act on its findings, so every critical issue has an owner and every alert reaches the SOC.

Key activities

- Close coverage gaps.

  - Connect remaining cloud accounts with Cloud Connect (agentless, read-only, least privilege).

  - Connect all in-scope repositories with GitHub Connect to find APIs and MCP servers in code.

  - Add traffic collectors at existing choke points: API gateways, load balancers, ingress controllers, CDN workers.

  - Confirm sensitive-field masking at collectors with privacy/legal.

- Assign ownership.

  - Tag crown-jewel APIs in Salt by business service.

  - Assign a business and technical owner to every crown-jewel API and every discovered MCP server.

  - Introduce the "no owner, no production" rule for new assets.

- Integrate with existing workflows.

  - Send consolidated, attacker-level alerts to the SIEM/SOAR.

  - Route posture findings to each team's ticketing backlog with severity and target date.

  - Write starter SOC runbooks: credential stuffing, BOLA/data scraping, sensitive data exposure.

- First risk reduction.

  - Remediate or accept (with documented risk) the top 20 critical/high findings.

  - Decommission zombie APIs; onboard or retire shadow APIs.

- Reporting.

  - Build the baseline executive dashboard with the KPIs in this document.

Deliverables

- Onboarding runbook and checklist for new accounts, gateways and repos.

- Ownership register for crown-jewel APIs and MCP servers.

- SIEM/SOAR and ticketing integrations live.

- Three starter SOC runbooks.

- Baseline KPI dashboard and first monthly steering report.

Who is involved: Salt platform owner (lead), cloud/platform team, app-team owners, SOC, privacy/legal for masking sign-off; Deloitte (design, integration support, runbooks).

Gate — exit criteria

- ☐ 100% of in-scope cloud accounts, gateways and repos connected.

- ☐ 100% of crown-jewel APIs and discovered MCP servers have named owners.

- ☐ Salt alerts flowing to SIEM; posture findings flowing to ticketing.

- ☐ Top 20 critical/high findings remediated or formally risk-accepted.

### Phase 3 — Govern and AI-SPM foundations (weeks 6–14)

Objective: turn findings into an enforced, repeatable governance process, and bring AI agents and MCP servers under the same posture controls as APIs.

Key activities

- Posture policy set.

  - Agree 8–12 enforced API policies (e.g. authentication on all external APIs, no sensitive data in responses, spec matches live traffic).

  - Add the five AI starter policies from "Extending Salt to AI security".

  - Document each policy: rule, severity, owner, exception process.

- Remediation model.

  - Agree SLAs by severity with engineering leadership (example: critical 7 days, high 30 days; to confirm with [Client]).

  - Define an exception and risk-acceptance workflow with expiry dates.

- Shift left.

  - Add Salt posture checks to CI/CD for priority repositories.

  - Start in warn mode; move to break-the-build for critical policies once teams are ready.

- AI agent and MCP register (AI-SPM).

  - Run MCP Finder across external surface, code and runtime traffic.

  - Reconcile results with the AI landscape scan from Phase 1.

  - Record for each agent and MCP server: owner, purpose, tools exposed, data touched, authentication, environment.

  - Flag and remediate unauthenticated or over-privileged MCP servers.

- Governance cadence.

  - Start the monthly posture review with app-team leads.

Deliverables

- Posture policy catalogue (API and AI) with exception process.

- Remediation SLA model approved by engineering leadership.

- CI/CD integration pattern and rollout plan.

- AI agent and MCP server register, with risk ratings.

- Monthly posture trend report.

Who is involved: Salt platform owner and CISO (policy approval), engineering leadership (SLAs), app and AI teams (remediation, register), DevOps (CI/CD); Deloitte (policy design, AI-SPM methodology, register build).

Gate — exit criteria

- ☐ Policy catalogue and SLAs approved and enforced in Salt reporting.

- ☐ CI/CD checks live for all crown-jewel repositories.

- ☐ AI agent and MCP register complete; every entry owned.

- ☐ All production MCP servers enforce authentication, or have a dated remediation plan.

### Phase 4 — Detect AI threats (weeks 10–20)

Objective: detect attacks on LLM applications and AI agents in real time, and give the SOC the context and runbooks to respond.

Key activities

- Enable AI Detection and Response.

  - Turn on AI-DR for priority LLM applications and agent workflows, in monitor mode.

  - Confirm detection coverage for direct and indirect prompt injection, jailbreaks and unsafe model behavior.

- Integrate existing AI controls.

  - Bring current AI guardrails and AI gateways into the Salt view.

  - Define the system of record for each control to avoid duplicate alerts.

- Agent behavior baselining.

  - Let Salt baseline normal tool and API usage per agent.

  - Define high-risk deviations to alert on (e.g. bulk data export, new tools, unusual systems of record).

- SOC readiness.

  - Write AI runbooks: prompt injection, jailbreak, agent off-script behavior, unauthenticated MCP access, bulk data export by an agent.

  - Train SOC analysts to triage with the Agentic Security Graph: prompt → MCP tool call → API → data affected.

  - Run one tabletop exercise on an agent-driven data exfiltration scenario.

- Tuning.

  - Review alerts weekly with app and AI owners.

  - Record every suppression with a reason and expiry date.

  - Track true-positive rate per application.

Deliverables

- AI-DR enabled on priority apps, with coverage matrix.

- AI runbook set integrated into SOAR.

- Tabletop exercise report and lessons learned.

- Detection tuning log and alert-quality report per application.

Who is involved: SOC (lead for runbooks and triage), Salt platform owner (enablement, tuning), AI and app teams (baselines, validation), AI platform owners (guardrails); Deloitte (detection engineering, runbooks, tabletop facilitation).

Gate — exit criteria

- ☐ AI-DR live on all priority LLM apps and agent workflows.

- ☐ AI runbooks signed off by the SOC lead; tabletop completed.

- ☐ Alert quality meets the agreed threshold for each app proposed for blocking.

- ☐ Median time to triage AI alerts under 1 hour.

### Phase 5 — Protect and sustain (weeks 18–26)

Objective: move from detecting to stopping high-confidence attacks, extend coverage across the estate, and hand over a self-sustaining operating model.

Key activities

- Monitor-to-block rollout.

  - Agree per-app blocking criteria: alert quality threshold met, owner approval, rollback plan tested.

  - Enable blocking through the WAF [Client] already runs (e.g. AWS WAF or CDN WAF), starting with one crown-jewel app.

  - Block unauthenticated MCP access at the edge where supported.

  - Expand app by app, reviewing impact for one to two weeks before the next.

- Extend coverage.

  - Onboard remaining in-scope apps, new cloud accounts and new agent platforms using the Phase 2 onboarding runbook.

  - Add new AI use cases to the AI register as they are proposed, before production.

- Continuous improvement.

  - Review policies, suppressions and runbooks quarterly.

  - Track new Salt capabilities and assess them against the roadmap.

- Handover.

  - Transfer runbooks, dashboards and governance cadence to [Client] owners.

  - Confirm staffing for steady state (platform owner, SOC coverage, app champions).

  - Present the six-month value report to the CISO and steering committee.

Deliverables

- Blocking criteria and per-app rollout log, with rollback plans.

- Updated coverage report across the estate.

- Steady-state operating model and runbook pack.

- Six-month value report against the KPI baseline.

- Next-year roadmap recommendations.

Who is involved: Salt platform owner and CISO (block decisions), SOC, cloud/network team (WAF), app owners (approval, validation); Deloitte (rollout planning, value report, handover).

Gate — exit criteria

- ☐ Blocking live on all crown-jewel apps with no unresolved business impact.

- ☐ 100% of in-scope assets covered, including new agent platforms.

- ☐ Steady-state ownership and staffing accepted by [Client].

- ☐ Six-month value report delivered and accepted by the steering committee.

## Extending Salt to AI security

Salt's distinctive value for AI is the agent "action layer": the MCP servers, tools and APIs that agents use to act on business systems. Model-level guardrails alone do not see this layer.

| Use case | Salt capability | What [Client] gets |
| --- | --- | --- |
| Find shadow AI | MCP Finder: external, code and runtime discovery | Register of MCP servers, the tools they expose and the data they touch |
| Stop risky AI before release | GitHub Connect with traffic-free risk scoring | MCP and API risks flagged in code, before deployment |
| AI posture (AI-SPM) | MCP posture management across agents, MCP servers and LLM integrations | Misconfigured or unauthenticated MCP servers flagged against policy |
| Detect attacks on LLM apps | AI Detection and Response (AI-DR) within Agentic Detection and Response | Real-time detection of direct and indirect prompt injection and jailbreaks |
| Catch agents going off-script | Intent Analysis and behavioral baselining | Alerts when an agent suddenly exports data in bulk or calls unusual tools |
| Trace an attack end to end | Agentic Security Graph | Path from malicious prompt to MCP tool call to API and data affected |
| Block at the edge | Salt with AWS WAF, incl. blocking unauthenticated MCP access | Automated blocking using the WAF [Client] already runs |

Recommended starter AI posture policies

- Every production MCP server requires authentication.

- Every agent and MCP server has a named business and technical owner.

- Agent tool scopes follow least privilege; no broad write access to systems of record.

- No sensitive data (PII/PHI, secrets) returned to agents without an approved use case.

- New agents and MCP servers are inventoried before they reach production.

Salt should complement, not replace, [Client]'s existing AI guardrails and AI gateways; Salt brings their signals into one view and correlates them with API activity.

## Operating model

Salt needs a named platform owner and clear hand-offs to app teams and the SOC; without them findings accumulate. R = responsible, A = accountable, C = consulted, I = informed.

| Activity | CISO | Salt platform owner | App and AI teams | Cloud / platform | SOC |
| --- | --- | --- | --- | --- | --- |
| Roadmap and priorities | A | R | C | C | C |
| Coverage and onboarding | I | A | C | R | I |
| Asset ownership | I | A | R | C | I |
| Posture policies | A | R | C | C | I |
| Posture remediation | I | C | A / R | R | I |
| Detection tuning | I | A | C | I | R |
| Incident response | I | C | C | C | A / R |
| Monitor-to-block decisions | A | R | C | C | C |

Cadence

- Weekly: Salt working session (platform owner, app champions, SOC lead).

- Monthly: steering committee with the CISO; KPI dashboard review.

- Quarterly: policy review and roadmap refresh.

## Measuring value

We propose eight KPIs for the monthly executive dashboard. Baselines are captured in the first 30 days; targets are proposals for agreement.

| KPI | Definition | Proposed target (month 6) |
| --- | --- | --- |
| Coverage | In-scope cloud accounts, gateways and repos connected to Salt | 100% |
| Ownership | Crown-jewel APIs, agents and MCP servers with a named owner | 100% |
| Critical exposure | Open critical/high posture findings | Down 50% from baseline |
| Remediation SLA | Critical/high findings fixed within SLA | 90% or higher |
| Shadow AI | Agents and MCP servers found outside the approved register | Trending down after month 3 |
| MCP authentication | Production MCP servers enforcing authentication | 100% |
| Detection quality | AI-DR and API alerts confirmed as true positives | Meets agreed threshold |
| Protection | Crown-jewel apps with automated blocking enabled | 100% of priority apps |

## Decisions needed and how Deloitte can support

Four decisions from [Client] unlock the roadmap.

- ☐ Name a Salt platform owner with dedicated capacity.

- ☐ Confirm the crown-jewel application list and AI/agent scope.

- ☐ Approve the remediation SLA model with engineering leadership.

- ☐ Agree the criteria for moving applications from monitor to block.

Deloitte support options

| Option | Scope | Typical duration |
| --- | --- | --- |
| A. Salt health check | Discovery workshop, coverage gap analysis, maturity assessment, prioritized backlog | 2–3 weeks |
| B. Operationalize and govern | Option A plus quick wins, SIEM/ticketing integration, posture policies, runbooks, KPI dashboard | 8–12 weeks |
| C. AI security program | Option B plus AI agent and MCP inventory, AI posture policies, AI-DR enablement, monitor-to-block rollout, operating model hand-over | ~6 months |

Proposed next step: schedule the 2-hour discovery workshop to validate the current state and confirm scope for the preferred option.

## Assumptions and risks

Assumptions: Salt is licensed for the capabilities referenced (including MCP discovery and AI-DR; to confirm with Salt and [Client] procurement); [Client] can provide app-team and SOC time; timelines are planning estimates.

| Risk | Mitigation |
| --- | --- |
| Incomplete onboarding leaves blind spots | Coverage KPI; onboarding checklist for every new account, gateway and agent platform |
| Findings pile up without owners | "No owner, no production" rule; ownership KPI |
| Blocking too early disrupts legitimate traffic | Monitor-first; per-app block decision with rollback plan |
| Posture alone misses live agent misuse | Pair AI-SPM with runtime AI-DR and agent behavior baselines |
| SOC alert fatigue | Attacker-level alerts; tuned runbooks; suppressions with expiry |
| Overlap with existing guardrails or CNAPP | Define a system of record per control; integrate rather than duplicate |

## Sources

- Salt Security — Agentic Security Platform

- Salt AI Detection and Response announcement

- Salt MCP Finder

- Salt GitHub Connect

- Salt MCP Security Blueprint

- Salt and AWS integration