## DRL Gap Update
Phase | Request | Status | Documents Received | Gap / Follow-up Ask | Priority
P1 | AI governance policies, standards & procedures | Partial | AI Governance Policy (Sept 2026 DRAFT); AI Risk Subcommittee Charter; GenAI Risk Assessment Template V3; GenAI Use Case Submission form | • AI use-case inventory (we received the intake form, not the list of use cases) • AI risk register • AI governance org structure / RACI | Medium
P1 | Parent (TMNA) AI governance & security policy | Partial | TMNA AI & ML Policy | • Mapping between TMNA policy and TMCC standards. This drives D4/D5 scoping (standalone TMCC standard vs. an implementation layer under TMNA) | Medium
P1 | Existing AI security tooling & guardrails inventory | Partial | AI Tool Capabilities FY27 v2; ADR GenAI Platform Bedrock Guardrails Design | • DLP / redaction tooling • AI monitoring tooling • System access documentation for direct tool review | Medium
P2 | Existing draft AI security architecture patterns | Not Received | — | • ~7 existing patterns referenced by Ben Taylor (Aug 19). Core input for D2/D3 • Supporting diagrams, control lists, applicability notes | High
P2 | Agentic AI & MCP usage documentation | Partial | EDP-ADR10026 (Agentic App Architecture & Standards) + 10026A–D (Environment, Memory, Evaluation, Tool Use) | • MCP server inventory (owners, deployment locations, tools exposed) | High
P2 | Third-party LLM access (AWS Bedrock) | Partial | Bedrock Gen AI Platform SCP; AWS Bedrock Default Settings | • Credential / key management approach • List of BUs / applications consuming Bedrock | Medium
P2 | AI gateway architecture & technology | Received | GenAI Gateway API Integration Guide; TFS Enterprise AI Platform Gateway Services (RAG & Chat); MuleSoft API Proxy for GenAI; GenAI Gateway Phase 1 Architecture & Roadmap | • Confirm whether MuleSoft is the gateway of record or interim | Low
P2 | MCP proxy architecture documentation | Partial | Kiro – MCP ADR Test | • Production / target MCP proxy architecture (current doc is a test ADR) • How MCP-specific controls differ from LLM gateway controls | Medium
P2 | AI-powered IDE / agentic dev environment usage | Not Received | — | • Approved IDEs / tools in use (Kiro referenced in the MCP ADR, so usage likely exists) • Governance / config standard, autonomy-mode defaults, approval workflows • Controls: workstation/tool lockdown, CLI logging, blocked sharing/external access | High
P2 | Agentic AI embedded in third-party SaaS | Not Received | — | • Confirm whether SaaS-embedded agents are in use (e.g., CRM/analytics agents) • Deployment model and feature toggles per platform | Medium
P2 | Customer-facing AI chatbot documentation | Not Received | — | • Confirm whether a chatbot exists or it was not shared • If one exists: architecture, action capability, red-team results | Medium
P2 | Internal AI assistant usage | Partial | Enterprise RAG Platform Auth Design; Enterprise RAG AuthN/AuthZ Design; ADR-003 Hybrid RAG; ADR-004 Connector Framework | • Access-control audit results for RAG • Confirm other internal assistants in use (e.g., M365 Copilot) | Low
P2 | Agentic identity & access management (IAM) program | Partial | Offboarding Lifecycle – Harness IaCM Pipeline | • Received doc appears off-target (infra offboarding pipeline) • Need agentic IAM program docs. Coordinate via Sarthak Patel / Trent & David | Medium
P2 | Security architecture patterns from parallel engagement (Mandiant) | Not Received | — | • Mandiant-produced patterns, per Ben Taylor (to come via Ben) • Needed to avoid duplication with D2 | High
P3 | Existing draft AI security standard | Received | AI Security Standard.docx | • Prior stakeholder feedback / socialization notes | Low
P3 | AI security exception process documentation | Not Received | — | • Current exception process, if any • Historical exceptions granted | Medium
P4 | AI/MCP gateway vendor landscape & tooling in use | Not Received | — (partially covered by P2 Gateway docs) | • Prior vendor evaluations, RFPs, or scoring exercises | Medium
P4 | Existing agentic AI & API security platform config (SALT) | Not Received | — | • Licensed tier (posture mgmt + detection/response vs. legacy API tier) • Network placement (edge vs. east-west) • MCP-server discovery coverage • System access / session with AI Security Manager | High
P4 | Existing AI/MCP gateway selection criteria | Not Received | — | • Expected empty. Confirm none exists; D6 will be built from scratch | Low
P2 | (Not requested) Questionnaires | Received | Document Bot use case 1.pdf | • None. Useful as a sample use case for pattern validation | —
Legend:
Received
Partial
Not Received
Source: TMCC response to DRL, reviewed 2026-09-21